## GanttChart
DSCI 560-Project Schedule <teamName>
Team:
| Project Start Date: |  |  | 2021-10-28 | time axis 2021-10-25 to 2022-01-16
| Display Week: |  |  | 1 |  |  |  |  | 2021-10-25: Week 1; 2021-11-01: Week 2; 2021-11-08: Week 3; 2021-11-15: Week 4; 2021-11-22: Week 5; 2021-11-29: Week 6; 2021-12-06: Week 7; 2021-12-13: Week 8; 2021-12-20: Week 9; 2021-12-27: Week 10; 2022-01-03: Week 11; 2022-01-10: Week 12
[9 empty] | 2021-10-25 | [6 empty] | 2021-11-01 | [6 empty] | 2021-11-08 | [6 empty] | 2021-11-15 | [6 empty] | 2021-11-22 | [6 empty] | 2021-11-29 | [6 empty] | 2021-12-06 | [6 empty] | 2021-12-13 | [6 empty] | 2021-12-20 | [6 empty] | 2021-12-27 | [6 empty] | 2022-01-03 | [6 empty] | 2022-01-10
WBS | Task | Lead | Prede cessor | Start | End | Cal. Days | % Done | Work Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Phase 1 | [Name]
1.1 |  | [Name] |  | 2021-10-28 | 2021-10-30 | 3 | 60% | 2 | bar: 2021-10-25 T to 2021-10-25 S
1.2 | P1 |  |  | 2021-10-28 | 2021-11-01 | 5 | 10% | 5 | bar: 2021-10-25 T to 2021-11-01 M
1.3 | P1 |  |  | 2021-10-30 | 2021-11-01 | 3 | 0% | 1 | bar: 2021-10-25 S to 2021-11-01 M
1.4 | P1 |  |  | 2021-11-01 | 2021-11-02 | 2 | 10% | 2 | bar: 2021-11-01 M to 2021-11-01 T
1.5 | P1 |  |  | 2021-11-03 | 2021-11-04 | 2 | 200% | 2 | bar: 2021-11-01 W to 2021-11-01 T
1.6 | P1 |  |  | 2021-11-05 | 2021-11-06 | 2 | 300% | 1 | bar: 2021-11-01 F to 2021-11-01 S
1.7 | P1 |  |  | 2021-11-07 | 2021-11-07 | 1 | 400% | 0 | bar: 2021-11-01 S
1.8 | Complete JSMF Post-Doc application |  |  | 2021-11-01 | 2021-11-12 | 12 | 500% | 10 | bar: 2021-11-01 M to 2021-11-08 F
1.9 | Submisison Deadline JSMF Post-Doc application |  |  | 2021-11-01 | 2021-11-13 | 13 | 600% | 10 | bar: 2021-11-01 M to 2021-11-08 S
2 | Phase 2
2.1 | P2 |  |  | 2021-11-08 | 2021-11-09 | 2 | 60% | 2 | bar: 2021-11-08 M to 2021-11-08 T
2.2 | P2 |  |  | 2021-11-10 | 2021-11-12 | 3 | 20% | 3 | bar: 2021-11-08 W to 2021-11-08 F
2.3 | P2 |  |  | 2021-11-13 | 2021-11-13 | 1 | 10% | 0 | bar: 2021-11-08 S
2.4 |  |  |  | 2021-11-14 | 2021-11-14 | 1 | 0% | 0 | bar: 2021-11-08 S
2.5 |  |  |  | 2021-11-15 | 2021-11-15 | 1 | 0% | 1 | bar: 2021-11-15 M
2.6 |  |  |  | 2021-11-16 | 2021-11-16 | 1 | 0% | 1 | bar: 2021-11-15 T
2.7 |  |  |  | 2021-11-17 | 2021-11-17 | 1 | 0% | 1 | bar: 2021-11-15 W
2.8 |  |  |  | 2021-11-18 | 2021-11-19 | 2 | 0% | 2 | bar: 2021-11-15 T to 2021-11-15 F
2.9 |  |  |  | 2021-11-20 | 2021-11-21 | 2 | 0% | 0 | bar: 2021-11-15 S to 2021-11-15 S
2.10 |  |  |  | 2021-11-22 | 2021-11-22 | 1 | 0% | 1 | bar: 2021-11-22 M
2.11 |  |  |  | 2021-11-23 | 2021-11-25 | 3 | 0% | 3 | bar: 2021-11-22 T to 2021-11-22 T
2.12 |  |  |  | 2021-11-26 | 2021-11-28 | 3 | 0% | 1 | bar: 2021-11-22 F to 2021-11-22 S
2.13 |  |  |  | 2021-11-29 | 2021-12-01 | 3 | 0% | 3 | bar: 2021-11-29 M to 2021-11-29 W
2.14 |  |  |  | 2021-12-02 | 2021-12-03 | 2 | 0% | 2 | bar: 2021-11-29 T to 2021-11-29 F
2.15 |  |  |  | 2021-12-04 | 2021-12-05 | 2 | 0% | 0 | bar: 2021-11-29 S to 2021-11-29 S
2.16 | [Insert Rows above this one, then Hide or Delete this row]
3 | Optical Testing
3.1 | Continue Shadowing Vinh |  |  | 2021-10-28 | 2021-11-15 | 19 | 5% | 13 | bar: 2021-10-25 T to 2021-11-15 M
3.2 | Get Qualified to Test devices solo |  |  | 2021-11-11 | 2021-11-30 | 20 | 5% | 14 | bar: 2021-11-08 T to 2021-11-29 T
3.3 | Analyze data and Assist with manuscript preparation |  |  | 2021-12-01 | 2021-12-20 | 20 | 0% | 14 | bar: 2021-11-29 W to 2021-12-20 M
3.4 | Refine test procedure and retest |  |  | 2021-12-21 | 2021-12-25 | 4 | 0% | 4 | bar: 2021-12-20 T to 2021-12-20 S
3.5 | [Insert Rows above this one, then Hide or Delete this row]
4 | GUV testing
4.1 | Refine procedure for generating and plating GUVs |  |  | 2021-12-23 | 2022-01-03 | 12 | 0% | 8 | bar: 2021-12-20 T to 2022-01-03 M
4.2 | Apply Di-4 and vary test to achieve consistency |  |  | 2022-01-04 | 2022-01-13 | 10 | 0% | 8 | bar: 2022-01-03 T to 2022-01-10 T
4.3 | Analyze data and repeat as neccesary |  |  | 2022-01-14 | 2022-01-21 | 8 | 0% | 6 | bar: 2022-01-10 F to 2022-01-10 S
4.4 | [Task] |  |  | 2022-01-15 | 2022-01-15 | 1 | 0% | 0 | bar: 2022-01-10 S
4.5 | [Insert Rows above this one, then Hide or Delete this row]
5 | Molecular Dynamics modelling
5.1 | Start trial to embed hexane molecule in POPC membrane patch |  |  | 2021-12-13 | 2021-12-26 | 14 | 0% | 10 | bar: 2021-12-13 M to 2021-12-20 S
5.2 | Generate model for Di-4 and calibrate forces for compatibility with membrane patch |  |  | 2021-12-27 | 2022-01-09 | 14 | 0% | 10 | bar: 2021-12-27 M to 2022-01-03 S
5.3 | Analyze data and repeat as neccesary |  |  | 2022-01-10 | 2022-01-16 | 7 | 0% | 5 | bar: 2022-01-10 M to 2022-01-10 S
.1 | [Insert Rows above this one, then Hide or Delete this row]
.2 | [ Level 2 Task ]
.2.1 | . [ Level 3 Task ]
.2.1.1 | . . [ Level 4 Task ]
Examples of ways to define the Start, End, and Duration of tasks
1 | [ Task Category (summary) ] |  |  | 2015-03-01 | 2015-03-01 | 1 |  | 0
2 | Milestone |  |  | 2015-03-01 | 2015-03-01
2.1 | [ Start Date and Calendar Days ] | [6 empty] | 0
2.2 | [ Start Date and End Date ] |  |  |  |  | 0 |  | 0

## GanttChartPro (hidden)
Gantt Chart Template Pro
Gantt Chart Template Pro is similar to this free version, but
it is more feature-packed. It also comes with other bonus content.
Learn More About Gantt Chart Template Pro
http://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
The following link is a blog post that talks specifically about the
Pro version for Excel Online.
Gantt Chart Template Pro for Excel Online
Benefits and Features of Gantt Chart Template Pro
Daily, Weekly, or Monthly View
The Pro version includes a drop-down next to the Display Week that lets you choose to display
the columns in the chart area as days, weeks, or months.
Use Work Days as an Input
By default, the Pro version is set up to have you enter Work Days instead of Calendar Days.
The expanded set of template rows provides more options for defining the Start date, End date,
and Duration of tasks. Define a task based on …
- Start date and End date
- Start date and Work days
- Start date and Calendar days
Easily Create Task Dependencies
Though you can still use your own formulas for creating task dependencies,
the Pro version includes template rows that calculate the Start date based
on the WBS number that you enter in the Predecessor column.
Exclude Holidays from Work Days
List holidays and other specific non-working days that you want to exclude from work days.
Customize Your Work Week
The Pro version for Excel Online uses the WORKDAY.INTL() and NETWORKDAYS.INTL()
functions that allow you define the work week as something other than Monday-Friday.
Simple Color-Coding
The Pro version includes a column for specifying the color of bars in the chart. For example,
you could change the color based on urgency or task lead.
Learn More About Gantt Chart Template Pro

## Help
HELP
Version: Gantt Chart Template for Office 365 - FREE Version
Intro
This Gantt Chart spreadsheet is designed to to help you create a simple project schedule. You
only need to know some basic spreadsheet operations, such as how to insert, delete, copy and
and paste rows and cells. For more advanced uses, such as defining task dependencies, you
will need to know how to enter formulas.
Be sure to read the Getting Started Tips below. Watching the video demos for Gantt Chart Template Pro may also help you see how to use the spreadsheet.
Watch Demo Videos on Vertex42.com
Before sharing this spreadsheet, please read the license agreement in the TermsOfUse worksheet.
Getting Started Tips
| - Input cells for defining the task dates and durations have a light green background. | Input Cell
- [ Bracketed Text ] is meant to be edited, like the project title and task descriptions.
| - Some of the labels include cell comments to provide extra help information. | Label
- The Project Start Date determines the first week shown in the gantt chart.
- To adjust the range of dates shown in the gantt chart, change the Display Week.
- To insert a new task, insert a new row, then copy/paste a row from the selection of template
rows at the bottom of the worksheet, depending on how you want to define the task.
- If you see "#####" in a cell, widen the column to display the cell contents.
- Backup your file regularly to avoid losing data! Excel files get corrupted occasionally.
Using the Template Rows and Choosing a WBS Level
Inserting New Tasks.
1. Insert a new blank row where you want the new task to be.
2. Copy the entire row you want to use from the set of template rows.
3. Paste the row you copied on top of the new row you just inserted.
4. Copy and paste the WBS cell separately, based on the level (1, 1.2, 1.2.3, 1.2.3.4)
Important: When inserting new rows, you must copy and paste an entire row, because the cells of the Gantt chart area are formulas.
Changing the WBS Level in the WBS Column
- The WBS numbering uses a different formula for each level, but the formula does not reference any other cell in the row. So, you can copy and paste just the WBS cell that you want to use.
- If you leave a blank cell above a WBS number, the numbering will reset to 1.x.x. The formulas are meant for convenience, but you can manually enter them if you need to.
- You can indent the task description for sub-tasks by entering leading spaces or using the Indent feature in Excel.
Category Tasks
- You can use tasks that are just labels, but it may be useful for a category task to display the minimum Start date and maximum End date of its sub tasks. This can be done using =MIN(range_of_startdates) and =MAX(range_of_enddates).
Creating Task Dependencies
- You can enter the Start date manually, or define task dependecies using a formula. Below are the most common options for defining the Start date:
A. | Enter the date manually (e.g. 1/3/2015)
B. | Reference the Project Start Date (e.g. =$E$4 )
C. | Set the Start date to the next Work Day after another task's End date.
- Use the formula =WORKDAY(enddate,1) where enddate is the reference to the End date of a predecessor task.
- For multiple predecessors, the formula would be =MAX(WORKDAY(enddate1,1),WORKDAY(enddate2,1))
D. | Set the Start date to the next Calendar Day after another task's End date.
- This formula is very simple: =enddate+1
- For multiple predecessors, the formula would be =MAX(enddate1,enddate2,enddate3 )+1
E. | Set the Start date to a number of days before or after another date.
- This formula is just like the one in C or D, except that in place of the "1" you enter the number of days, such as =WORKDAY(enddate,5) or =WORKDAY(startdate,-5)
E. | Use the Predecessor column to start the day after another task
[ Template rows that use this feature are only in the PRO version ]
Changing the End Date Font to Red when Behind Schedule
[ This feature is only in the PRO version, but if you are familiar with conditional formatting, you could try doing this yourself. ]
Changing the Color of the Bars in the Gantt Chart
[ This feature is only in the PRO version. ]
FAQs
Q: | How do I enter the Work Days instead of Calendar Days?
Entering work days instead of calendar days is one of the main features of the Pro version. If you want to figure it out on your own, use the WORKDAY() function to define the End Date and calculate the Calendar Days based on the Start and End dates.
Q: | How do I calculate the %Complete for an entire category of tasks?
The %Complete for a category task can be calculated from its sub tasks using the formula below, where "workdays" is a reference to the range of work day values and "complete" is a reference to the %complete for each of the subtasks.
=SUMPRODUCT(workdays,complete)/SUM(workdays)
Example: =SUMPRODUCT(G9:G15,I9:I15)/SUM(G9:G15)
Let's say you have 3 sub tasks that are 10 days, 12 days, and 14 days long, respectively. If the first subtask is 50% complete and the others are 25% complete, you could calculate the overall percent complete for the group as: =(10*50%+12*25%+14*25%)/(10+12+14).
Q: | How do I change the Print Settings? (Excel 2010, 2013)
Select the entire range of cells you want to print and go to File > Print Area > Set Print Area.
Then go to File > Page Setup or File > Print Preview and adjust the Scaling, Marings, and
Page Orientation as desired.
Q: | The Start date, End date, or %Complete for a Level 1 task is wrong. How do I fix it?
When using =MIN(), =MAX(), and =SUMPRODUCT(), it is easy for the references to get messed up if you move rows around or insert new rows. You should verify and fix these formulas if they are not referencing the correct ranges.
Example: The image below shows that the MIN() function is not referencing all of the sub tasks.
Q: | I've messed up the chart area somehow. How do I fix it?
Find a row that works, then copy the cells that make up the gantt chart area from that row into the row that is messed up.
© 2015 Vertex42 LLC

## TermsOfUse (hidden)
Gantt Chart Template
http://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
By Vertex42.com
© 2006-2015 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
See License Agreement
http://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet. If necessary, you may hide it by right-clicking on the tab and selecting Hide.